## Defect_Log
S.No. | Sprint | Defects Details | Steps to reproduce | Issues severity(as per mantis) | Reported date
1 | Sprint 1 | Clicking on verification link received is not taking the user to LMS Dash board. | 1. Login to the Email provided at the time of registering in to LMS web app. 2. Click on the verification link received in mail Actual: user should be navigated to LMS dash board |  | 2020-07-02
2 | Sprint 1 | User is unable to login using the registered Email and password. | 1. After completing LMS registration==>go to LMS login page. 2. Enter valid Email and password==>Click submit Actual: User should be able to login to LMS web app. |  | 2020-07-02
3 | Sprint 1 | Existing user validation alert messages are not displayed in User name, Email fields when user try to re register. | 1. Click on register in LMS login page. 2. Enter existing user name and Email Actual: User should be displayed with a toast message stating "This user name already exists", "This Email already exists" |  | 2020-07-02
4 | Sprint 1 | Taking little more time in receiving verification link mail to mail id's other than Cintana. | There is a bit more time taken in receiving verification link mail to mail id's other than Cintana mail. |  | 2020-07-02
5 | Sprint 2 | Text fields in register form is not getting cleared when showing message "User Account already exist ? Thank You" for both CMS/LMS. | 1. Login to LMS / CMS register form fill existing user details in to the form. 2. Click sign up. 3. Verify whether the text fields are getting cleared after user receives the message "User Account already exist ? Thank You". Actual: Text fields are not getting cleared after showing the toast message. |  | 14/2/2020
6 | Sprint 2 | User is not able to access "Log in" from "Sign up" page. log in not enabled in CMS / LMS sign up page. | 1. Try to click on "Login" displayed in "Sign up" page of CMS or LMS. Actual: User is not able to access "Log in" from "Sign up" page. log in not enabled in CMS / LMS sign up page. |  | 14/2/2020
7 | Sprint 2 | Field level validation errors not displayed in LMS / CMS when user click "Sign up" without filling the form. | 1. Login to LMS / CMS==>Click on Sign up without filling any of the fields in the Sign up form. Actual: Field level validation errors not displayed in LMS / CMS when user click "Sign up" without filling the form. |  | 14/2/2020
8 | Sprint 2 | User is not getting the message, "verification link has been sent to your Email" after completing clicking on sign up in LMS or CMS. | 1. Login to LMS / CMS==>Click on register==>Fill all the mandatory fields in the sign up form. 2. Click on submit. 3. Verify whether user receives a message like ""verification link has been sent to your Email" Actual: User is not getting the message, "verification link has been sent to your Email" after completing clicking on sign up in LMS or CMS. |  | 14/2/2020
9 | Sprint 2 | LMS user is able to login to CMS | 1. Create registered users in both LMS and CMS. 2. Now go to CMS and try to login to login with LMS user credentials. Actual: LMS user is able to login to CMS |  | 14/2/2020
10 | Sprint 3 | User is able to land in Admin dashboard after clicking on back button from login page. | 1. Login to Admin dashboard using valid credentials 2. Click on logout button displayed in Admin dashboard. 3. After logging out==>Click on back button from login page. Actual: User is able to land in Admin dashboard after clicking on back button from login page. |  | 18/2/2020
11 | Sprint 3 | incorrect spelling "Inavlid, Invalid Login Credentials" while entering invalid password in Admin login. | 1. Enter a valid Email and an invalid password in Admin login screen. 2. Click submit. Actual: Incorrect spelling "Inavlid, Invalid Login Credentials" while entering invalid password in Admin login. |  | 18/2/2020
12 | Sprint 3 | No error message displayed for invalid Email and valid password combination in Admin login. | 1. Enter an invalid Email and a valid password in Admin login screen. 2. Click submit. Actual: No error message displayed for invalid Email and valid password combination in Admin login. |  | 18/2/2020
13 | Sprint 3 | Please clear field level error messages once user clears the erraneous data from fields. | 1. Enter an invalid Email format and an invalid password in Admin login acreen. 2. Delete the input entered after field level error / alert messages are displayed. Actual: Field level error messages are not getting cleared once user clears the erraneous data from fields. |  | 18/2/2020
14 | Sprint 3 | User is able to login to Admin dashboard by entering the url : http://18.218.96.173/adminDashboard | 1. Launch the url http://18.218.96.173/admin==>login with valid login credentials==>logout from Admin dashboard. 2. Now change the url to http://18.218.96.173/adminDashboard Actual: User is able to login to Admin dashboard by entering the url : http://18.218.96.173/adminDashboard Access to dashboard should be made only through log in with valid credentials. |  | 18/2/2020